## Defect Data
Release | Field Defects per kLOC | Product Verification Defects per kLOC
1 | 50 | 206
1.1 | 58 | 268
1.2 | 66 | 375
Total | 174 | 849

## Defect Breakdown
Defect Type | Field | Product Verification | Total
Interface | 69.6 | 339.6 | 409.2
Performance | 34.8 | 127.35 | 162.15
Capacity | 34.8 | 169.8 | 204.6
Other | 34.8 | 212.25 | 247.05

## Gantt Chart
Task | Start (Week Number) | Duration (Weeks)
Software Development Phase | 0 | 13
Test Preparation Phase | 0 | 13
Product Verification Phase | 13 | 17
Write Framework (Jane) | 0 | 8
Test Preparation (Jane) | 8 | 13
Test Execution (Jane) | 21 | 9
Test Preparation (Dave) | 0 | 10
Test Preparation (Steve) | 0 | 10
Automate Tests (Dave and Steve) | 10 | 3
Test Execution (Software Developer) | 22 | 4